## Ark1
Lofthus frukt og saft. Project Schedule
Project start date: 18.11.2019
Project end date: 29.11.2019
*(30min) Iteration meetings: Every Monday 08:30 (For developers)
*(10min) Daily standups: every day at 10:00 (For developers and stakeholders)
TASK | LEAD | START | END | DAYS | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Main meny |  |  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S
Research for main meny | Ahmed(Front-end) | 2019-11-18 | 2019-11-20 | 3 | bar: M to W
- Collect client vision and goals | Ida(Front-end) | 2019-11-19 | 2019-11-20 | 2 | bar: T to W
- Reshearch comp. brands | Ahmed(Front-end) | 2019-11-18 | 2019-11-19 | 2 | bar: M to W
- Clarify brand strategy | Ole(Copywriter) | 2019-11-19 | 2019-11-21 | 3 | bar: T to T
Color & Graphics
- Color and Graphics | Henrik(Front-end Designer) | 2019-11-20 | 2019-11-22 | 3 | bar: W to F
Presentation of content
- Common fonts | Henrik(Front-end Designer) | 2019-11-22 | 2019-11-23 | 2 | bar: F; M
- Font sizes, font colors | Henrik(Front-end Designer) | 2019-11-22 | 2019-11-23 | 2 | bar: F; M
Functionality
- External hyperlinks | Ahmed(Front-end) | 2019-11-25 | 2019-11-26 | 2 | bar: M to T
- Script errors | Ahmed(Front-end) | 2019-11-26 | 2019-11-27 | 2 | bar: T to W
- Form functionality | Ida(Front-end) | 2019-11-25 | 2019-11-26 | 2 | bar: M to T
Prototype
- Prototype |  | 2019-11-27 | bar: W
Browser compatibility
-Test in Firefox | Ahmed(Front-end) | 2019-11-28 | 2019-11-29 | 2 | bar: T to F
Chrome | Ahmed(Front-end) | 2019-11-28 | 2019-11-29 | 2 | bar: T to F
Safari | Ida(Front-end) | 2019-11-28 | 2019-11-29 | 2 | bar: T to F
IE | Ida(Front-end) | 2019-11-28 | 2019-11-29 | 2 | bar: T to F